## Sheet1
📊 Gantt Chart – Tri’s Chess Project
Task | Week 1 | Week 2 | Week 3 | Week 4 | Week 5 | Week 6 | Week 7 | Week 8 | Week 9 | Week 10
Research & Planning | Week 1: ▓▓▓▓▓; Week 2: ▓▓▓▓▓; Week 3: ▓▓▓▓▓
Setup Pygame & Board Drawing | Week 4: ▓▓▓▓▓; Week 5: ▓▓▓▓▓
Import & Scale Piece Images | Week 4: ▓▓▓▓▓; Week 5: ▓▓▓▓▓
User Input & Move Handling | Week 4: ▓▓▓▓▓; Week 5: ▓▓▓▓▓
Integrate Pretrained AI | Week 8: ▓▓▓▓▓
Game Over Detection & Testing | Week 9: ▓▓▓▓▓; Week 10: ▓▓▓▓▓
Fix Bugs | Week 6: ▓▓▓▓▓; Week 7: ▓▓▓▓▓; Week 9: ▓▓▓▓▓